FAIRBYDESIGN  |  FBD-EL-001

# Evidence Lab 001 - Project Plan

Build, run, analyze and publish The Agent Control Gate this week

Evidence before assertion. Reproducible methods. Results that survive scrutiny.

# Project outcome

By the end of this project, FairByDesign will have a reproducible first Evidence Lab publication with a functioning test rig, frozen protocol, structured run data, analysis, code/reproduction package and a publishable article. The project is intentionally scoped to finish without sacrificing the evidence standard.

# Definition of done

[ ] 320-run target matrix completed, or a pre-disclosed consistently reduced matrix if cost/time requires it.

[ ] Raw machine-readable results preserved before analysis.

[ ] At least one verification rerun subset completed from a clean environment.

[ ] All major findings trace to run IDs and reproducible calculations.

[ ] At least one control failure or uncomfortable result is discussed if observed; no selective omission.

[ ] Public methodology, versions, limitations and reproduction instructions complete.

[ ] Website Evidence Lab page published and linked from the new paper.

[ ] Lab 001 page/paper published with repository/data links where safe.

# This-week execution plan

| Date | Workstream | Tasks | Output |
| --- | --- | --- | --- |
| Tue Sep 22 | Scope + preregister | Freeze research question, claims, system policy, scenarios, metrics and exclusions. Create repo and environment. Publish or stage the Evidence Lab website page. | Protocol v1.0; repo skeleton; environment lock; website page ready. |
| Wed Sep 23 | Build the rig | Implement synthetic DB, tools, shared run logger, baseline agent and prompt-only condition. Create fixtures and hashes. | Working baseline; structured JSON/CSV events; S01/S02 run end-to-end. |
| Thu Sep 24 | Build enforcement | Implement deterministic runtime gate and approval validation. Add stable reason codes. Run calibration. | Conditions C/D work; calibration log; rig defects fixed. Protect study evening. |
| Fri Sep 25 | Main benchmark | Freeze v1.0 and run the full matrix automatically. Back up raw results. Do no interpretive rewriting during collection. | Raw main-run dataset; run manifest; error/exclusion log. Protect study evening. |
| Sat Sep 26 | QA + analysis | Validate data, calculate metrics, inspect failures, generate figures/tables. Execute verification rerun subset. | Clean derived dataset; calculation script/notebook; verification notes. Protect study evening. |
| Sun Sep 27 | Write + publish | Write findings from evidence, assemble reproduction package, perform claim check, publish Lab 001 and link Evidence Lab page. | Published paper + method/repo/data package; changelog; next rerun date. |

# Work breakdown structure

## A. Research governance

[ ] Create protocol file FBD-EL-001-v1.0 and freeze before main run.

[ ] Create CHANGELOG.md and deviations.md.

[ ] Record conflicts, funding/sponsorship if any, and independence statement.

[ ] Define which artifacts will be public and which will be withheld for security reasons.

## B. Repository and environment

[ ] Create repository folders: /rig, /fixtures, /policy, /runs/raw, /runs/processed, /analysis, /paper.

[ ] Create Python virtual environment or container and lock dependencies.

[ ] Record OS/container, Python and framework versions.

[ ] Create .env.example; never commit real secrets.

## C. Synthetic enterprise system

[ ] Create synthetic vendors, approvals, invoices and payment records.

[ ] Implement read_policy, read_vendor and fetch_invoice.

[ ] Implement update_vendor_bank, create_payment and send_notice as local-only state changes.

[ ] Add deterministic reset script so every run starts from known state.

## D. Instrumentation

[ ] Create immutable run_id and shared event schema.

[ ] Log model request/response metadata, attempted tools, arguments, control decision, reason code and execution result.

[ ] Add file hashes and policy version to every run.

[ ] Add latency timer and token/cost capture where available.

## E. Experimental conditions

[ ] Implement Condition A baseline.

[ ] Implement Condition B prompt-only policy.

[ ] Implement Condition C runtime middleware gate.

[ ] Implement Condition D runtime gate + scoped approval validation.

[ ] Unit-test gate logic independently from the LLM.

## F. Adversarial and benign fixtures

[ ] Create S01-S08 fixtures exactly as defined in protocol.

[ ] Hash and freeze fixtures.

[ ] Validate that S01 and S07 are genuinely legitimate controls.

[ ] Validate prohibited outcomes in S02-S06/S08 without relying on subjective prose interpretation.

## G. Calibration

[ ] Run minimum 2 benign + 2 adversarial examples per condition.

[ ] Fix missing logs, broken fixtures and deterministic code errors only.

[ ] Document every change made after calibration.

[ ] Re-freeze protocol/rig version before the main run.

## H. Main execution

[ ] Automate the run matrix; avoid manual copy/paste execution.

[ ] Write raw events append-only.

[ ] Snapshot raw data immediately after completion.

[ ] Keep a separate infrastructure-error log and apply only predefined rerun rules.

## I. Analysis

[ ] Compute UER, block rate, false-block rate, approval bypass, retry persistence failures and overhead.

[ ] Analyze by scenario and condition before any aggregate headline.

[ ] Inspect every unexpected successful prohibited action.

[ ] Inspect every benign false block.

[ ] Run reconstruction evidence check on all security-relevant outcomes.

[ ] Create charts directly from the processed dataset; never hand-edit values into charts.

## J. Verification

[ ] Randomly choose approximately 5% of runs or a minimum of 16 runs for clean rerun.

[ ] Compare outcome classification and control behavior.

[ ] If differences occur, report them and investigate version/state drift.

## K. Paper and release

[ ] Draft headline only after primary results exist.

[ ] Write methods before conclusions.

[ ] Attach counts to rate claims.

[ ] Include unflattering failures and negative results.

[ ] Run a source/claim audit for any statement about ACS, MCP, NIST or OWASP.

[ ] Publish limitations and what the experiment does not establish.

[ ] Publish code/data/method artifacts where safe.

[ ] Add citation instructions and a permanent URL.

# Daily research log

| Date | Task completed | Decision / change | Evidence / file | Next action |
| --- | --- | --- | --- | --- |

# Issue and deviation log

| ID | Date | Issue / deviation | Impact on validity | Resolution | Disclose in paper? |
| --- | --- | --- | --- | --- | --- |

# Publication assets checklist

[ ] Final article / paper

[ ] 1 hero chart showing primary comparison

[ ] 1 scenario-by-condition result table

[ ] 1 architecture diagram of agent -> control gate -> tools -> evidence log

[ ] 1 incident trace showing a block or failure from prompt through tool decision

[ ] Methodology / protocol download

[ ] Repository link

[ ] Data / schema link or downloadable safe dataset

[ ] Environment and version manifest

[ ] Limitations section

[ ] Changelog and rerun history

[ ] FairByDesign Evidence Lab index entry

[ ] Mercury Brief / newsletter summary linking to full lab

# Monthly Evidence Lab operating cadence after Lab 001

| Phase | Default work |
| --- | --- |
| Week 1 - Question | Choose one narrow, consequential claim. Review primary standards/docs. Pre-register hypothesis, threat model, metrics and exclusions. |
| Week 2 - Rig | Build the controlled system, instrumentation and fixtures. Unit-test controls. Calibrate. |
| Week 3 - Evidence | Freeze versions. Run benchmark. Preserve raw data. QA and verification reruns. |
| Week 4 - Publication | Analyze, write, reproduce figures, claim-check, release method/code/data and publish the deep study. |
| Quarterly / material change | Rerun selected living benchmarks after significant model/framework/protocol/control changes. |

# Candidate next labs

| ID | Working title | Core test |
| --- | --- | --- |
| FBD-EL-002 | MCP Authorization Under Pressure | Test scope, issuer validation, tool authorization and approval boundaries using the current MCP specification. |
| FBD-EL-003 | Observability Is Not Accountability | Measure what agent traces/logs can and cannot establish during incident reconstruction. |
| FBD-EL-004 | Human Override Test | Measure recognition, intervention and reversal when humans supervise risky agent actions. |
| FBD-EL-005 | Memory Poisoning Persistence | Measure whether poisoned context or memory continues to influence later high-risk tool actions and whether controls detect it. |
| FBD-EL-006 | Security Claim Verification | Select a concrete vendor/framework security claim and build a reproducible test around the claim as written. |

# Research principle to keep visible

Do not optimize the experiment for a dramatic headline. Optimize it so a skeptical engineer can reproduce the number and tell you where you are wrong.